## Project Management Plan
|  | add 1 hr |  | doc review b4 meeting | AS and AL add 1.3
|  | Weekly |  | On site | AS, AB, JG, JS add 2
|  | Virtual |  | Alliance add 1 or 2 | AL, TN add 1
| 2019-01-29 | 2019-01-30 | 2019-01-31 | 2019-02-01 |  | Project Management Plan Workload Distribution
Anthony Spencer (Group Leader) | ? | 2.5 | 2.5 | 3.5 |  | 8.5
Alexander Baselice |  |  | 1.5 | 3 |  | 4.5
Alexander Lundin | 2.5 | 1 | 1 | 2.5 |  | 7
Jairo Galarza |  | 1 | 2 | 2 |  | 5
Joseph Samonte | 1 |  |  | 2 |  | 3
Tony Nhan |  | 1 | 3 | 1 |  | 5

## Requirements Specification
|  | add 1 hr | [9 empty] | Team | All add 2
|  | Weekly | [9 empty] | meeting
|  | Virtual | [9 empty] | new building
| 2019-02-04 | 2019-02-05 | 2019-02-06 | 2019-02-07 | 2019-02-08 | 2019-02-09 | 2019-02-10 | 2019-02-11 | 2019-02-12 | 2019-02-13 | 2019-02-14 | 2019-02-15 |  | Requirements Specification Workload Distribution
Anthony Spencer (Group Leader) | 2019-02-05: 1; 2019-02-15: 2 |  | 3
Alexander Baselice | 2019-02-05: 1; 2019-02-15: 2 |  | 3
Alexander Lundin | 1.6 | 1.2 | 1 | 1.5 | 0.5 | 1.4 |  |  | 0.5 |  |  | 2 |  | 9.7
Jairo Galarza | 2019-02-05: 1; 2019-02-15: 2 |  | 3
Joseph Samonte | 2019-02-05: 1; 2019-02-07: 1; 2019-02-10: 1; 2019-02-11: 1; 2019-02-15: 2 |  | 6
Tony Nhan | 2019-02-05: 1; 2019-02-08: 1; 2019-02-15: 2 |  | 4

## Architecture Documentation
|  |  |  | add 1 hr |  |  |  | All 1.5 hr |  |  | All 1.75 hr
|  |  |  | Weekly |  |  | Weekly | JS add 1 hr |  |  | Weekly
|  |  |  | Virtual |  |  | in person | missing AB |  |  | in person
| 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | Architecture Documentation Workload Distribution
Anthony Spencer (Group Leader) | 2019-02-19: 2; 2019-02-22: 1.5; 2019-02-26: 1.75; 2019-02-27: 1.75; 2019-02-28: 1.75; 2019-03-01: 1.25 | 10
Alexander Baselice | 2019-02-19: 1; 2019-02-26: 1.75; 2019-02-28: 0.5; 2019-03-01: 0.5 | 3.75
Alexander Lundin | 0.5 |  | 1.5 | 1 |  |  | 2 | 3.5 | 0.666 |  | 1.75 | 2 |  | 1 | 13.916
Jairo Galarza | 2019-02-19: 1; 2019-02-22: 1.5; 2019-02-26: 1.75; 2019-02-28: 1; 2019-03-01: 0.15 | 5.4
Joseph Samonte | 2019-02-19: 1; 2019-02-22: 1; 2019-02-26: 2.25 | 4.25
Tony Nhan | 2019-02-22: 1; 2019-02-26: 1.75; 2019-02-27: 2; 2019-02-28: 2.5 | 7.25

## Detailed Design Documentation
|  |  |  | add 1 hr |  |  |  | add
|  |  |  | Weekly |  |  | Weekly | AS, AL 2
|  |  |  | Virtual |  |  | In person | JG, TN 1.5
| 2019-03-02 | 2019-03-03 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-09 | 2019-03-10 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | Detailed Design Documentation Workload Distribution
Anthony Spencer (Group Leader) | 2019-03-05: 1; 2019-03-08: 2 | 3
Alexander Baselice | [14 empty] | 1 | bar: 2019-03-05
Alexander Lundin | 2019-03-04: 0.75; 2019-03-05: 1.75; 2019-03-07: 0.62; 2019-03-08: 2 | 5.12
Jairo Galarza | 2019-03-05: 1; 2019-03-08: 1.75 | 2.75
Joseph Samonte | [14 empty] | 1 | bar: 2019-03-05
Tony Nhan | 2019-03-05: 1; 2019-03-08: 1.75 | 2.75