## Sheet1
Traditional | [5 empty] | Agile
Level 1 | Level2 | Level 3 | Level 4 | Level 6 | Level 7 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1
Milestone Name | Categories | Work Packages | Estimations | Actual | Status | 2018-03-31 | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29
Wireless Additions | Floor Plan | Create linetype | 0.1 | 0.3 | 1 |  |  | 0.3
|  | Print Example pdf | 0.1 | 0.3 | 1 |  |  | 0.3
| Riser | Restructure - wireless bridge on vertical rung | 1 | 9 | 1 |  |  |  |  | 1 | 8
|  | Restrucutre - add additional wireless segement type | 1 | 1 | 1 |  |  |  |  | 1
|  | Restructure- draw viewports around all segments | 1 | 1 | 1 |  |  |  |  | 1
| Room Details | Restructure - group occupancy and interfaces on their own rung | 1 | 1 | 1 |  |  |  |  | 1
|  | Restructure - 2 rungs from the Bridge | 4.5 | 4.5 | 1 | [6 empty] | 4.5
|  | Restructure - tighten all coordinate shifts | 4.5 | 4.5 | 1 | [6 empty] | 4.5
|  | Restrucutre - add wireless controller rung | 2 | 1 | 1 | [11 empty] | 1
|  | Restrucutre - add wireless device rung | 2 | 1 | 0 | [11 empty] | 1
| Relative Paths | Addition - String Constants File | 2 | 4.5 | 1 | 4.5
|  | Restructure- legacy code | 2 | 4.5 | 1 |  | 4.5
|  | Restructure- library code | 2 | 2 | 1 | [9 empty] | 2
|  | Restrucutre - callable functions | 2 | 2 | 1 | [9 empty] | 2
| Testing and Release | Unit Tests, Regression Tests, Test Cases | 3 | 0 | 1
|  | Document Test Profile Usage | 1 | 0 | 0
|  | Install Alpha (first release) for 3 engineers | 1.5 | 0 | 0
|  | Beta (second release) for 9 engineers | 3 | 0 | 0
|  | Golden Copy (live environment code) release steps for all | 3 | 0 | 0
| Recofigurations Between Release | Submittal 2.0 | 3 | 2 | 0 | [9 empty] | 1 |  | 1
|  | Alpha | 3 | 0 | 0
|  | Beta | 1.5 | 0 | 0
|  | Golden Copy | 0 | 0 | 1
| Planning | Create Burndown from Existing Data | 2 | 2 | 1 | [8 empty] | 2
|  | Continue to log | 1 | 0 | 1
|  | Total Days |  |  | 30
|  | Ideal Task Burndown |  |  | 19 | 18.3667 | 17.7333 | 17.1 | 16.4667 | 15.8333 | 15.2 | 14.5667 | 13.9333 | 13.3 | 12.6667 | 12.0333 | 11.4 | 10.7667 | 10.1333 | 9.5 | 8.8667 | 8.2333 | 7.6 | 6.9667 | 6.3333 | 5.7 | 5.0667 | 4.4333 | 3.8 | 3.1667 | 2.5333 | 1.9 | 1.2667 | 0.63333 | 0
|  | Tasks Remaining |  |  | 7
|  | Logged Effot |  |  |  | 4.5 | 4.5 | 0.6 | 0 | 4 | 8 | 9 | 0 | 2 | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Effort | 47.2 |  |  | 42.7 | 38.2 | 37.6 | 37.6 | 33.6 | 25.6 | 16.6 | 16.6 | 14.6 | 9.6 | 9.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6
|  | Ideal Effort Burndown | 47.2 |  |  | 45.6267 | 44.0533 | 42.48 | 40.9067 | 39.3333 | 37.76 | 36.1867 | 34.6133 | 33.04 | 31.4667 | 29.8933 | 28.32 | 26.7467 | 25.1733 | 23.6 | 22.0267 | 20.4533 | 18.88 | 17.3067 | 15.7333 | 14.16 | 12.5867 | 11.0133 | 9.44 | 7.8667 | 6.2933 | 4.72 | 3.1467 | 1.5733 | 0